## Slide 1: 3.3.4 Critical path analysis
Theme 3: Business decisions and strategy
How long does it take to make a cup of tea?
Fill kettle – 15 seconds
Boil kettle – 2 ½ minutes
Get mug out – 10 seconds
Get tea pot out – 10 seconds
Get milk out – 15 seconds
Get tea bag out – 10 seconds
Put milk in mug – 5 seconds
Put tea bag in tea pot – 5 seconds
Brew – 3 minutes
Pour – 10 seconds

## Slide 2: 3.3.4 Critical path analysis
In this topic you will learn about
  Nature and purpose of Critical Path Analysis
  Complete and interpret simple networks to identify the critical path
  Calculate:
    Earliest Start Time
    Latest Finish Time
    Total float
  Limitations of using Critical Path Analysis

## Slide 3: Critical path analysis
Critical path analysis is a technique used to identify the order in which all activities need to be completed when planning a complex project.
Critical path diagrams organise the activities in an order to show which activities can be done simultaneously and which are dependent upon earlier activities.
This allows for the identification of the shortest time in which a project can be completed.
The critical path is the set of activities that will lengthen the duration of the project if delayed.

## Slide 4: Critical path diagrams
A network diagram is made up of nodes
Each node is split into 3 parts
The node number, based upon the order in which it is drawn.
The earliest start time (EST) - the earliest the following activity can possibly start.
The latest finish time (LFT) – the latest an activity can finish without delaying the whole project.

## Slide 5: Critical path diagrams
Each activity is shown on a line that connects the nodes
The activity letter is shown above the line
The activity duration is shown below the line
Here activity A takes 4 weeks
A
4

## Slide 6: Completing a Critical path diagram
1
0
2
4
3
9
A
B
4
7
7
4
7
5
6
F
G
H
C
D
E
5
3
10
5
8
4
Node 1 always starts at 0
EST is calculated from left to right by adding the duration of the activity to the previous EST i.e. node 2 is 0 + 4 = 4. Node 3 is 4 + 5 = 9.
Complete the EST for activity F only.
Notes: 6

## Slide 7: Completing a Critical path diagram
1
0
2
4
3
9
A
B
4
7
7
4
7
5
11
6
19
F
G
H
C
D
E
5
3
10
5
8
4
4) The EST for activity F is 7 + 4 = 11.
5) When two or more activities go into the same node the highest number goes in the EST section.
6) Node 6 therefore has two paths leading to it – from activity C 4 + 10 = 14, from activity G 11 + 8 = 19. Therefore 19 goes in node 6.
7) Fill in the EST for node 7.
Notes: 7

## Slide 8: Completing a Critical path diagram
1
0
2
4
3
9
A
B
4
7
7
24
24
4
7
5
11
6
19
19
F
G
H
C
D
E
5
3
10
5
8
4
8) Node 7 – Activity E 9 + 3 = 12, activity H 19 + 5 = 24. Therefore 24 goes in node 7.
9) The LFT of the final node always matches the EST. Therefore node 7 the LFT is 24.
10) To complete the LFT you calculate from right to left. 24 – 5 duration of activity H = 19.
11) Calculate the LFT for nodes 3, 5 and 7.
Notes: 8

## Slide 9: Completing a Critical path diagram
1
0
2
4
9
3
9
21
A
B
4
7
7
24
24
4
7
7
5
11
11
6
19
19
F
G
H
C
D
E
5
3
10
5
8
4
12) Node 5 19 – 8 = 11. Node 4 11 – 4 = 7. Node 3 24 – 3 = 21.
13) When two or more activities go into the same node the lowest number goes in the LFT section.
14) Node 2 activity D 21 – 5 = 16, activity C 19 – 10 = 9. Therefore 9 goes in node 2.
15) Fill in the LFT on node 1.
Notes: 9

## Slide 10: Completing a critical path diagram
1
0
0
A
B
4
7
7
24
24
4
7
7
5
11
11
6
19
19
F
G
H
C
D
E
5
3
10
5
8
4
16) Node 1 will always have an EST of 0 and an LFT of 0.
17) Mark on the critical path – the path taken where EST = LFT.
18) The critical path is BFGH. If any of the activities along this path are delayed the whole project will be delayed.
2
4
9
3
9
21
Notes: 10

## Slide 11: Critical path analysis – the rules
Each line represents an activity
ESTs are calculated from left to right by adding the duration to the previous EST
If more than one activity precedes a node the highest figure becomes the EST
LFTs are calculated from right to left by subtracting the duration from the previous LFT
If more than one activity precedes a node the lowest figure becomes the LFT
The first node will always have an EST and LFT of zero
The final node will always have an EST and LFT that is the same figure
A node preceding an activity that is on the critical path will always have an EST and LFT that is the same
The critical path are those activities that must be completed on time if the whole activity is not to be delayed. These are identified by putting a line through the activity.

## Slide 12: ACTIVITY – Critical path analysis
1
0
2
7
3
9
17
A
B
6
9
7
25
4
9
5
12
12
6
F
G
H
C
D
E
3
8
14
4
9
3
Fill in the empty ESTs and LFTs on this diagram. Show the critical path by putting a line through each activity.
Notes: 12

## Slide 13: ACTIVITY – Critical path analysis
1
0
0
2
6
7
3
9
17
A
B
6
9
7
25
4
9
9
5
12
12
6
21
F
G
H
C
D
E
3
8
14
4
9
3
25
21
Notes: 13

## Slide 14: Network analysis
Non-critical activities are those which are not on the critical path
There is some leeway (spare time) to complete the activities
These activities are said to have float time
The total float for an activity can be found using the formula:
LFT – duration – EST
2
4
9
3
9
21
D
5
The total float for activity D is 21 – 5 – 4 = 12.
Total float is the amount of time an activity can be delayed without impacting on the whole project.

## Slide 15: Practice time
Complete the critical path diagram to show ESTs, LFTs and the critical path.
What is the total float for activity E?
What happens to the critical path if activity C is delayed by 2 weeks?

## Slide 16: Limitations of using critical path analysis
Is only a starting point for a successful project
Can not stop unexpected delays from happening
Relies on estimations of the duration of each activity
Does not take into account external influences
May encourage inefficient behaviour on non critical activities
Large projects can be too complex for CPA

## Slide 17: 3.3.4 Critical path analysis
In this topic you have learnt about
  Nature and purpose of Critical Path Analysis
  Complete and interpret simple networks to identify the critical path
  Calculate:
    Earliest Start Time
    Latest Finish Time
    total float
  Limitations of using Critical Path Analysis