| Q1 | Fill in the Gaps |
| --- | --- |
| A ____________ ____________ is often used by organisations when they have ___________ projects to undertake. These projects could be a marketing campaign, expansion of a factory or retail outlet or relocation to a new country. The use of network diagrams allow a business to not only ensure the projects are _____________ _____________ but, they are completed in the most ______________ and ______________ _________ possible. It is essential that a business identifies the minimum amount of time needed for a project to be completed and whether there is any likelihood of any ___________ that will impact the deadline set. Network diagrams will also show the business the activities that are ____________ to complete on time. This is known as the _____________ __________. These activities are identified where the earliest start time and the latest finish time are the same. |  |
|  | Choose from: critical path; network diagram; delays; critical; complex; efficient; managed effectively; quickest time |

| Q2 | Define the following terms |  |
| --- | --- | --- |
|  | 2.1 Earliest start time: |  |
|  | 2.2 Latest finish time: |  |
|  | 2.3 Critical path: |  |
|  | 2.4 Network diagram: |  |
|  | 2.5 Nodes: |  |
|  | 2.6 Total float: |  |

| Q3 | Complete the network diagram using the TWO columns of data below! Identify the EST, LFT and the critical path for this project |
| --- | --- |
| Activity; Length Weeks; Activity; Length Weeks. A; 2; F; 3. B; 10; G; 3. C; 6; H; 5. D; 4; I; 1. E; 5; J; 5. D A 2 4 J G E B 3 5 10 5 6 I 1 3 F C H 5 |
| Critical Path = |  |

| Q4 | The Operations Director has stated that he does not believe that some of the tasks have been correctly identified in terms of their length of time. He believes that Activity C should take 8 weeks, Activity F should take 8 weeks and Activity G should take 5 weeks. Complete the NEW network diagram below, identifying the EST, LFT and the critical path, as a result of these changes. (The table below has been updated as a result of these changes!) |
| --- | --- |
| Activity; Length Weeks; Activity; Length Weeks. A; 2; F; 8. B; 10; G; 5. C; 8; H; 5. D; 4; I; 1. E; 5; J; 5. D A 4 2 0 J G E B 0 10 5 5 5 I 1 8 F 8 C H 5 |
| Critical Path = |  |

| Q5 | Short answer questions… |
| --- | --- |
|  | 5.1 Identify three limitations of using critical path analysis 1. 2. 3. |
|  | 5.2 What is the impact on a construction business of not completing a project on time? |